## Scrum Project Management
Want more best practices? Visit www.Praxie.com
Scrum Project Management is a type of agile project management that involves leading a team from one sprint to the next using time-bound deliverables and action plans. Scrum Project Management is an iterative process that enables organizations to develop an iterative on the software development process more frequently. Each stage of Scrum Project Management is called a sprint, which typically lasts between a few days to a week or up to a month. During a sprint, the project team produces a specific deliverable, assesses the learning and results achieved, and then defines exactly what’s needed for the next sprint. Create your own Scrum plan using template below.
Scrum Project Management Template
| Individual/Organization Name: |  |  |  | Last Updated: | [6 empty] | Date:
| Backlog Item | Points | Assignee | Priority | Total Estimate Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total Actual Hours | Completion Date | Status | Comments
| SCRUM 1 | 60 |  |  | 60 | 13.75 | 13.5 | 21.75 | 0 | 0 | 49 | 2023-01-01
| Story A | 10 | Assignee A | HIGH | 10 | 1.25 | 2.5 | 3 |  |  | 6.75 | 2023-01-01 | 25%
| Story B | 20 | Assignee B | MEDIUM | 20 | 2 | 1 | 10.5 |  |  | 13.5 |  | 50%
| Story C | 30 | Assignee C | LOW | 30 | 10.5 | 10 | 8.25 |  |  | 28.75 |  | Not Started
| SCRUM 2 | 60 |  |  | 17.5 | 3.5 | 4 | 3.5 | 0 | 0 | 11 | 2023-01-01
| Story A | 10 | Assignee A | HIGH | 10 | 1 | 2 | 3 |  |  | 6 | 2023-01-01 | 25%
| Story B | 20 | Assignee B | MEDIUM | 5.5 | 2 | 1 | 0.5 |  |  | 3.5 |  | 50%
| Story C | 30 | Assignee C | LOW | 2 | 0.5 | 1 | 0 |  |  | 1.5 |  | Not Started
| SCRUM 3 | 60 |  |  | 17.5 | 3.5 | 4 | 3.5 | 0 | 0 | 11 | 2023-01-01
| Story A | 10 | Assignee A | HIGH | 10 | 1 | 2 | 3 |  |  | 6 | 2023-01-01 | 25%
| Story B | 20 | Assignee B | MEDIUM | 5.5 | 2 | 1 | 0.5 |  |  | 3.5 |  | 50%
| Story C | 30 | Assignee C | LOW | 2 | 0.5 | 1 | 0 |  |  | 1.5 |  | Not Started
Formulas:
Date: = MAX([Date:, row below]:M17)
Scrum Project Management Template